## data
project | phase | epic/goal | Fibonacci Complexity | % completed | converted score | done | remaining
ASL | Q2Q3 | Find a non-technical summary | 8 | 0% | 8 | 0 | 8
ASL | Q2Q3 | Cancel PIL | 8 | 0% | 8 | 0 | 8
ASL | Q2Q3 | View Establishment Details | 13 | 0% | 13 | 0 | 13
ASL | Q2Q3 | Log in and Manage Account | 13 | 0% | 13 | 0 | 13
ASL | Q2Q3 | Transfer Staff Licence from Establishment to Establishment | 13 | 0% | 13 | 0 | 13
ASL | Q2Q3 | Update Personal Details | 13 | 0% | 13 | 0 | 13
ASL | Q2Q3 | View Personal Licence Holders | 21 | 0% | 21 | 0
ASL | Q2Q3 | View Basic Details - PPL | 21 | 0% | 21 | 0
ASL | Q2Q3 | Apply for PIL | 21 | 0% | 21 | 0
ASL | Q2Q3 | Amend PIL | 34 | 0% | 34 | 0
| Total |  |  |  | 165
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0

## burnup data
Sprint start date | Sprint | Total Work | Predicted Velocity | Actual Velocity | Predicted Total Velocity |  | Actual Total Velocity
2018-05-02 | 7 | 165 | 6 | 0 | 6 | 2018-05-02 | 0
2018-05-16 | 8 | 165 | 6 |  | 12 | 2018-05-16
2018-05-30 | 9 | 165 | 6 |  | 18 | 2018-05-30
2018-06-13 | 10 | 165 | 6 |  | 24 | 2018-06-13
2018-06-27 | 11 | 165 | 6 |  | 30 | 2018-06-27
2018-07-11 | 12 | 165 | 6 |  | 36 | 2018-07-11
2018-07-25 | 13 | 165 | 6 |  | 42 | 2018-07-25
2018-08-08 | 14 | 165 | 6 |  | 48 | 2018-08-08
2018-08-22 | 15 | 165 | 6 |  | 54 | 2018-08-22
2018-09-05 | 16 | 165 | 6 |  | 60 | 2018-09-05
2018-09-19 | 17 | 165 | 6 |  | 66 | 2018-09-19
2018-10-03 | 18 | 165 | 6 |  | 72 | 2018-10-03
2018-10-17 | 19 | 165 | 6 |  | 78 | 2018-10-17
2018-10-31 | 20 | 165 | 6 |  | 84 | 2018-10-31
2018-11-14 | 21 | 165 | 6 |  | 90 | 2018-11-14
2018-11-28 | 22 | 165 | 6 |  | 96 | 2018-11-28
2018-12-12 | 23 | 165 | 6 |  | 102 | 2018-12-12
2018-12-26 | 24 | 165 | 6 |  | 108 | 2018-12-26
2019-01-09 | 25 | 165 | 6 |  | 114 | 2019-01-09
2019-01-23 | 26 | 165 | 6 |  | 120 | 2019-01-23
2019-02-06 | 27 | 165 | 6 |  | 126 | 2019-02-06
2019-02-20 | 28 | 165 | 6 |  | 132 | 2019-02-20
2019-03-06 | 29 | 165 | 6 |  | 138 | 2019-03-06
2019-03-20 | 30 | 165 | 6 |  | 144 | 2019-03-20
2019-04-03 | 31 | 165 | 6 |  | 150 | 2019-04-03
2019-04-17 | 32 | 165 | 6 |  | 156 | 2019-04-17
2019-05-01 | 33 | 165 | 6 |  | 162 | 2019-05-01
2019-05-15 | 34 | 165 | 6 |  | 168 | 2019-05-15
Formulas:
Sprint start date = [Sprint start date, row above]+14

## dashboard
Current date | 2018-04-23
Current Sprint | 8
Likely date of completion | 2019-05-01

## assessors questions (hidden)
questions
show the goal
what date? why this date?
AC for the goal
things needed to acheive teh goal?
who agreed these?
who sized them
where is the AC?
who is estimating the progress?
where is the plan? in jira?

## reporting audit (hidden)
report | recurrance | Project | author | owner | audience | link to report example | comments
example 1 | when its submitted | project a | who writes the content | Who should this be for? | who else gets it
example 2 |  | project b | who writes the content | Who should this be for? | who else gets it
Sprint Notes | Every two weeks | Agile Coaching Delivery | Delivery Manager | Service Manager | stakeholders, interested observers |  | Is useful but only as low level update. Doesnt show due date or report progress towards.
Sprint Notes | Every two weeks | Firearms | Delivery Manager | Service Manager | stakeholders, interested observers |  | sam stopped sending to real owners so a waste of time
Sprint Notes | Every two weeks | Proving Things To Government | Delivery Manager | Service Manager | stakeholders, interested observers |  | Is useful but only as low level update. Doesnt show due date or report progress towards.
Sprint Notes | Every two weeks | Passport Digital Customer Services | Delivery Manager | Service Manager | stakeholders, interested observers |  | Is useful but only as low level update. Doesnt show due date or report progress towards.
Sprint Notes | Every two weeks | IRC Bed Space Management | Delivery Manager | Service Manager | stakeholders, interested observers |  | Is useful but only as low level update. Doesnt show due date or report progress towards.
Sprint Notes | Every two weeks | Travel and Escorting (RMP) | Delivery Manager | Service Manager | stakeholders, interested observers |  | Is useful but only as low level update. Doesnt show due date or report progress towards.
None | Never | Digital Tools |  | Service Manager | stakeholders, interested observers
Sprint Notes | Monthly | Central Team | Delivery Manager | Service Manager | stakeholders, interested observers |  | Is useful but only as low level update. Doesnt show due date or report progress towards.
Sprint Notes | Never | Single Intelligence Platform | Delivery Manager | Service Manager | stakeholders, interested observers
sprint notes | Every two weeks | Sponsoring People | Delivery Manager | Service Manager | stakeholders, interested observers
Sprint Notes | Every two weeks | Syrian Refugee Resettlement Service | Delivery Manager | Service Manager | stakeholders, interested observers